## Progress
V1.2 (Week 9)
Tasks | PIC | PR Review PIC | Progress | PR Review | Components | PIC
Import interviewer's data | Rui Zhi | Cheng Seng | N | N | Storage (Import & Export) | Rui Zhi
Add interviewer and interviewee (manually) | Kendrick | Rui Zhi | N | N | Model | Kendrick & Rui Zhi
Display schedule | Cheng Seng | Kendrick | N | N | UI | Cheng Seng & Kendrick
Generate schedule from imported data (Basically it's to create the Schedule class) | Yau Dong | Zhong Jun | N | N | Schedule | Yau Dong
Email (individual) | Zhong Jun | Yau Dong | N | N | Email | Zhong Jun
[5 empty] | Parsing & Logic (linking of features) | Everyone
Notes
* Rui Zhi & Cheng Seng needs to work closely cuz the two components are very interrelated
* Everyone needs to write clear documentation to help each other understand each other's code
* Make the interface good so that even the underlying logic changes it won't cause too much changes
* Spend time to familarise & understand the component that you are in charge of
V1.3 (Week 11) |  |  |  |  | * Ask for help if needed, can ask others to help you implement some utility classes to faciliate your job if you can't handle
Tasks | PIC | PR Review PIC | Progress | PR Review
Import interviewee's data | Rui Zhi | Cheng Seng | N | N
Delete interviewer | Kendrick | Rui Zhi | N | N | Project Criteria (Team)
Display interviewee's data | Cheng Seng | Kendrick | N | N | Product Design | Cohesiveness of features
Schedule | Yau Dong | Zhong Jun | N | N
Storage (& Email individually) | Zhong Jun | Yau Dong | N | N
Update help link | Yau Dong |  |  |  | Project Criteria (Individual)
[5 empty] | 1) Implementation | Code quality
Feature Quality
[5 empty] | 2) Grading | System/Acceptance Testing
Developer Testing
[5 empty] | 3) Documentation | User Guide
Developer Guide
V1.4 (Week 13, Mon 2359) (this one is a BUFFER)
Tasks | PIC | PR Review PIC | Progress | PR Review | 4) Project Management | Milestone progress
Export csv file | Rui Zhi | Zhong Jun | N | N |  | Contribution to team tasks
UI Touch Up / More test cases | Cheng Seng | Kendrick (if UI Touch Up is done instead of test cases) | N | N
Delete interviewee | Kendrick | Rui Zhi | N | N | * Every PR someone must do sth
More test cases (Integration Testing & System Testing) | Zhong Jun | - | N | N
More test cases (Remaining Unit Testing & Integration Testing) | Yau Dong | - | N | N

## Features
What to have by v1.4 |  |  | Important Criteria
1) | Import, Export | Rui Zhi | Evaluate based on one biggest feature that you have done
2) | Display | Kendrick
3) | Schedule | Yau Dong | Import
4) | Add, Delete | Chen Sheng | Generate
5) | Email | Zhong Jun | Schedule
Export
Email
Import & Export
1) | Import interviewees's data | V1.2
2) | Import interviewer's data | V1.3
3) | Export schedule csv file | V1.4
Schedule
1) | Schedule interviews | V1.2
2) | Generate interview timeslots timetable (from interviewer's data) | V1.3
Displaying
1) | Display interview timeslots | V1.2
2) | Display interviewee's data | V1.3
3) | Display schedule | V1.4
Add, Delete
1) | Add interviewer | V1.2
2) | Add interviewee | V1.2
3) | Delete interviewer & corresponding timeslot | V1.3
4) | Delete interviewee & from the timeslot if assigned | V1.4
Email
1) | Send individual email (HTML) | V1.2
2) | Send mass email | V1.3